## Notes
Ernesto Gonzalez – Key Asks
Keep assessment fully data-driven → no opinions, only evidence-backed insights
First establish current state clearly before defining roadmap
Bring structure & clarity to:
Roles & responsibilities
Application ownership
Governance & reporting
Fix data inconsistencies → align to a single source of truth (CMDB)
Do not treat this as an audit → objective is structuring and organizing data
Be pragmatic in stakeholder engagement → targeted sampling, not exhaustive coverage
Be realistic on availability → limited involvement from product/business teams
Ensure joint accountability → Mondelez must not become a bottleneck
Shift mindset → from regional → product / function-based model
Prioritize high-value insights → avoid over-analysis (e.g., cost detail not immediate focus)
Drive fast & practical execution (~3 months) → avoid over-governance
Karol Jurcik – Key Asks
Assess AMS in context of product/platform transformation
Provide independent, external POV → challenge current state & assumptions
Evaluate AMS fit within product org (not just operations)
Highlight both gaps & strengths (balanced view)
Be realistic → product model is still early-stage and evolving

## Team Role Matrix
HCLTech Team Member | Project Role | Primary Accountability | Key Outputs Owned | Internal Cadence | Backup / Support | Critical Watchouts | First 2-Week Focus
Ankit Agarwal | Global Client Partner / Account Sponsor | Sponsor relationship, executive alignment, escalation support and strategic messaging | Executive alignment notes, sponsor messaging, escalation support | Steering / as needed | Niraj Upadhyay | Keep message aligned to SOW boundaries and non-audit posture | Support kickoff follow-up and sponsor alignment
Niraj Upadhyay | Engagement Lead | Overall engagement leadership, advisory storyline, quality control and client-facing delivery leadership | Integrated storyline, weekly leadership narrative, quality gate sign-off, executive readouts | Daily internal pulse + weekly governance | Rathindra Ghosh | Prevent over-engineering; keep short runway and pragmatic execution | Lock governance, data strategy, workshop sequencing and charter
Giridhar Krishnagiri | AMS SME | AMS architecture, application support model,ServiceNow, queues, ticket volumetrics, dashboard/reporting inventory and analysis | Application support model inputs, Queue inventory, ticket analysis, dashboard inventory, volumetrics fact pack | 2x weekly governance track | Shilpi Bhatnagar | Avoid assuming data completeness; validate through source evidence
Rathindra Ghosh | AMS Governance Lead | Governance, KPI, reporting, escalation and operating rhythm design | Governance cadence, meeting inventory, KPI framework, scorecard and comms charter | 2x weekly governance track | Giridhar Krishnagiri | Governance must be light-touch; avoid over-governance | Set governance model, weekly status template and meeting inventory approach
Shilpi Bhatnagar | AMS SME | ITIL / service delivery maturity assessment, process diagnostics and current-state synthesis, technical/process advisory | Current-state assessment sections, process maturity findings, pain point themes., technical maturity view, service architecture observations, | 2x weekly assessment sync | Giridhar Krishnagiri | Keep questions neutral; do not sound like audit | Build interview guides and current-state assessment structure, Define assessment data model and technical discovery approach
Shruthi Chandrashekar | Operating Model Lead | Product-aligned AMS operationalisation, role clarity, RACI and role profile design | AMS RACI, role profiles, role gap/overlap analysis, operating recommendations | 2x weekly design sync | Niraj Upadhyay | Do not redesign product model; operationalise decided model | Define RACI skeleton and role interview questions
Pratik Sathe | Business & Data Analyst - Benchmarking Lead | Benchmarking, process maturity, capacity/value hypotheses and AI/automation advisory support | Benchmark notes, capacity insights, automation opportunity inputs | Daily during data load | Narasimha Murthy | Tag data gaps and confidence; do not force conclusions from incomplete extracts, Use benchmarks as indicative only until evidence validated | Set data tracker, required extracts and analysis templates, Define maturity scale and benchmark lens
Pooja Kanungo | Business & Data Analyst - Application & Ownership | Application inventory, ownership matrix, Stakeholder Inventory, stakeholder mapping, workshop notes and synthesis | Application inventory, ownership matrix, stakeholder map, workshop minutes | Daily during discovery | Narasimha Murthy | Capture source and confidence for every input | Prepare inventory templates and stakeholder map v0.1
Narasimha Murthy | PMO and Business & Data Analyst - Transformation | PMO control tower, plan, RAID, action log, status updates, meeting cadence and document control | Project plan, RAID/action/decision logs, weekly status, workshop calendar, deliverable tracker | Daily internal control | Pooja Kanungo / Pratik Sathe | Keep a single source of truth; no parallel trackers | Finalize internal tracker, cadence, actions and first weekly status

## Workstream Ownership
WS | Workstream | Phase | Primary HCL Owner | Supporting Team | Core Internal Responsibilities | Committed Deliverables | Quality Reviewer | Internal Due / Gate (TBC) | Notes
WS1 | Mobilization and Transformation Structure | Phase 0 | Narasimha Murthy | Pooja, Pratik | Control tower, charter, project plan, governance, RAID, data discovery approach | Transformation charter; integrated project plan; data request tracker; RAID/action log; weekly status template | Niraj | 2026-06-12 | Foundation before assessment
WS2 | Current-State Baseline | Phase 1 | Shilpi Bhatnagar | Giridhar, Pooja, Pratik | Review artefacts, conduct interviews, synthesize pain points, risks, quick wins | Current-state assessment summary; current-state operating view; pain point and opportunity register; quick win recommendations | Niraj | 2026-07-24 | No audit posture; fact-based
WS3 | Data Gathering and Inventory Consolidation | Phase 1 | Giridhar Krishnagiri | Pooja, Narasimha, Shilpi | Gather, clean, structure and consolidate fragmented data into validation-ready inventories | Application support inventory; ownership matrix; ServiceNow queue inventory; queue-to-app-owner mapping; dashboard/reporting inventory; governance inventory; stakeholder map; team profile inventory | Niraj | 2026-07-24 | HCL heavy-lifting workstream
WS4 | Role Clarity, RACI and Operating Model Recommendations | Phase 2 | Shruthi Chandrashekar | Shilpi, Pooja, Narasimha | Clarify responsibilities, identify gaps/overlaps, operationalise product-aligned AMS model | AMS RACI matrix; target role profiles; role gap/overlap analysis; AMS 2.0 operating model recommendations | Niraj | 2026-08-28 | Operationalise decided product model; not greenfield redesign
WS5 | Governance, Communication and Reporting Framework | Phase 2 | Rathindra Ghosh | Giridhar, Pratik, Narasimha | Assess current governance and define future cadence, reporting, KPIs and communication standards | Future-state governance calendar; meeting rationalization; templates; communication charter; KPI framework; executive scorecard; dashboard requirements | Niraj | 2026-08-28 | Lightweight, decision-led governance
WS6 | Capacity and Demand Fact Base | Phase 2 | Giridhar Krishnagiri | Pratik, Shilpi | Map workload, criticality, ticket volumes, ownership, coverage and demand-supply gaps | Capacity and demand model; capacity heatmap; role/demand alignment view; capacity recommendations | Niraj | 2026-09-04 | No staffing decisions; fact base only
WS7 | Transformation Roadmap and Execution Support | Phase 3 | Niraj Upadhyay | Narasimha, Rathindra, Shruthi, Giridhar | Convert findings into sequenced roadmap, implementation backlog and final readout | AMS 2.0 roadmap; implementation backlog; quick win execution support plan; executive readout deck; final handover package | Ankit / Niraj | 2026-09-18 | Leadership-ready narrative
WS8 | AI and Automation Roadmap Advisory | Phase 3 | Giridhar Krishnagiri | Pratik, Shilpi | Assess automation maturity and identify prioritized advisory AI/automation opportunities | Automation maturity summary; AI/automation opportunity map; prioritized recommendations; agentic AI inputs; assumptions/dependencies register | Niraj | 2026-09-11 | Advisory only

## Deliverable Control
Deliverable Control Log
SOW-committed deliverables only (ownership, QA and approval readiness)
ID | Phase | Workstream | Deliverable | ID2 | Primary Owner | Support | Draft Due (TBC) | Final Due (TBC) | Status | QA Owner | Review Audience | Acceptance / Completion Evidence
D01 | Phase 0 | WS1 | AMS 2.0 Transformation Charter | D01 | Narasimha Murthy | Pooja | 2026-06-09 | 2026-06-12 | In Progress | Niraj | Ernesto, Karol, Tanveer | Charter reviewed and agreed
D02 | Phase 0 | WS1 | Integrated Project Plan | D02 | Narasimha Murthy | Niraj | 2026-06-09 | 2026-06-12 | In Progress | Niraj | Karol, Tanveer | Plan baselined
D03 | Phase 0 | WS1 | Data Request / Discovery Tracker | D03 | Narasimha Murthy | Pooja, Pratik | 2026-06-06 | 2026-06-12 | In Progress | Niraj | Karol, Tanveer, data owners | Tracker live
D04 | Phase 0 | WS1 | RAID / Action Log | D04 | Narasimha Murthy | Pooja | 2026-06-06 | 2026-06-12 | In Progress | Niraj | Karol, Tanveer | Log active
D05 | Phase 0 | WS1 | Weekly Status Update Template | D05 | Rathindra Ghosh | Narasimha | 2026-06-10 | 2026-06-12 | Not Started | Niraj | Karol, Tanveer | Template agreed
D06 | Phase 1 | WS2 | Current-State Assessment Summary | D06 | Shilpi Bhatnagar | Niraj, Pooja, Pratik | 2026-07-06 | 2026-07-12 | Not Started | Niraj | AMS leadership | Baseline validated
D07 | Phase 1 | WS2 | Current-State Operating View | D07 | Shilpi Bhatnagar | Pooja | 2026-07-06 | 2026-07-12 | Not Started | Niraj | AMS leadership | Operating view agreed
D08 | Phase 1 | WS2 | Pain Point and Opportunity Register | D08 | Pooja Kanungo | Shilpi | 2026-07-06 | 2026-07-12 | Not Started | Shilpi | AMS functional leads | Register validated
D09 | Phase 1 | WS2 | Quick Win Recommendations | D09 | Pratik Sathe | Shilpi | 2026-07-06 | 2026-07-12 | Not Started | Niraj | AMS leadership | Quick wins aligned
D10 | Phase 1 | WS3 | AMS Application Support Inventory | D10 | Pooja Kanungo | Pratik | 2026-06-18 | 2026-06-25 | Not Started | Niraj | AMS functional leads | Inventory exceptions captured
D11 | Phase 1 | WS3 | Application Ownership Matrix | D11 | Pooja Kanungo | Pratik | 2026-06-18 | 2026-06-25 | Not Started | Shruthi | AMS functional leads | Ownership gaps identified
D12 | Phase 1 | WS3 | ServiceNow Queue / Assignment Group Inventory | D12 | Giridhar Krishnagiri | Pooja, Pratik | 2026-06-18 | 2026-06-25 | Not Started | Niraj | ServiceNow SMEs | Queue inventory validated
D13 | Phase 1 | WS3 | Queue-to-App-to-Owner Mapping | D13 | Giridhar Krishnagiri | Pooja, Pratik | 2026-06-18 | 2026-06-25 | Not Started | Niraj | AMS functional leads | Mapping exceptions documented
D14 | Phase 1 | WS3 | Dashboard and Reporting Inventory | D14 | Pratik Sathe | Rathindra | 2026-06-18 | 2026-06-25 | Not Started | Rathindra | Reporting owners | Dashboard inventory validated
D15 | Phase 1 | WS3 | Governance and Meeting Inventory | D15 | Rathindra Ghosh | Narasimha | 2026-06-18 | 2026-06-25 | Not Started | Niraj | Karol / Tanveer | Meeting inventory validated
D16 | Phase 1 | WS3 | Stakeholder Map | D16 | Pooja Kanungo | Narasimha | 2026-06-18 | 2026-06-25 | Not Started | Niraj | Karol / Tanveer | Stakeholder map confirmed
D17 | Phase 1 | WS3 | Mondelez AMS Team Profile Inventory | D17 | Pooja Kanungo | Shilpi | 2026-06-18 | 2026-06-25 | Not Started | Narasimha | AMS functional leads | Team profile validated
D18 | Phase 2 | WS4 | AMS RACI Matrix | D18 | Shruthi Chandrashekar | Niraj, Shilpi | 2026-08-14 | 2026-08-28 | Not Started | Niraj | AMS leadership | RACI aligned for validation
D19 | Phase 2 | WS4 | Target Role Profiles | D19 | Shruthi Chandrashekar | Pooja | 2026-08-17 | 2026-08-28 | Not Started | Niraj | AMS leadership | Role profiles reviewed
D20 | Phase 2 | WS4 | Role Gap and Overlap Analysis | D20 | Shruthi Chandrashekar | Shilpi | 2026-08-14 | 2026-08-28 | Not Started | Niraj | AMS leadership | Gaps/overlaps agreed
D21 | Phase 2 | WS4 | AMS 2.0 Operating Model Recommendations | D21 | Shruthi Chandrashekar | Narasimha,Giridhar | 2026-08-21 | 2026-08-28 | Not Started | Niraj | Ernesto / AMS leadership | Recommendations aligned
D22 | Phase 2 | WS5 | Future-State Governance Calendar | D22 | Rathindra Ghosh | Narasimha | 2026-08-17 | 2026-08-28 | Not Started | Niraj | AMS leadership | Governance calendar reviewed
D23 | Phase 2 | WS5 | Meeting Rationalization Recommendations | D23 | Rathindra Ghosh | Narasimha | 2026-08-17 | 2026-08-28 | Not Started | Niraj | AMS leadership | Keep/change/retire view agreed
D24 | Phase 2 | WS5 | Governance Templates | D24 | Rathindra Ghosh | Narasimha | 2026-08-21 | 2026-08-28 | Not Started | Niraj | Karol / Tanveer | Templates packaged
D25 | Phase 2 | WS5 | Communication Charter | D25 | Rathindra Ghosh | Niraj | 2026-08-21 | 2026-08-28 | Not Started | Niraj | AMS leadership | Communication norms aligned
D26 | Phase 2 | WS5 | AMS KPI Framework | D26 | Rathindra Ghosh | Giridhar, Pratik | 2026-08-21 | 2026-08-28 | Not Started | Niraj | AMS leadership | KPI framework reviewed
D27 | Phase 2 | WS5 | Executive AMS Scorecard Template | D27 | Rathindra Ghosh | Pratik | 2026-08-21 | 2026-08-28 | Not Started | Niraj | AMS leadership | Scorecard template reviewed
D28 | Phase 2 | WS5 | Operational Dashboard Requirements | D28 | Pratik Sathe | Rathindra | 2026-08-21 | 2026-08-28 | Not Started | Rathindra | Reporting owners | Requirements documented
D29 | Phase 2 | WS6 | Capacity and Demand Model | D29 | Giridhar Krishnagiri | Pratik | 2026-08-24 | 2026-09-04 | Not Started |  | AMS leadership | Model reviewed
D30 | Phase 2 | WS6 | Capacity Heatmap | D30 | Giridhar Krishnagiri | Pratik, Shilpi | 2026-08-24 | 2026-09-04 | Not Started | Niraj | AMS leadership | Heatmap validated
D31 | Phase 2 | WS6 | Role / Demand Alignment View | D31 | Giridhar Krishnagiri | Shruthi, Pratik | 2026-08-24 | 2026-09-04 | Not Started | Niraj | AMS leadership | Alignment view reviewed
D32 | Phase 2 | WS6 | Capacity Recommendations | D32 | Giridhar Krishnagiri | Niraj | 2026-08-28 | 2026-09-04 | Not Started |  | AMS leadership | Recommendations captured
D33 | Phase 3 | WS8 | Automation Maturity Assessment Summary | D33 | Giridhar Krishnagiri |  | 2026-09-04 | 2026-09-11 | Not Started | Niraj | Automation stakeholders | Summary reviewed
D34 | Phase 3 | WS8 | AI and Automation Opportunity Map | D34 | Giridhar Krishnagiri | Pratik | 2026-09-04 | 2026-09-11 | Not Started | Niraj | Automation stakeholders | Opportunity map reviewed
D35 | Phase 3 | WS8 | Prioritized Automation Recommendations | D35 | Giridhar Krishnagiri | Niraj | 2026-09-08 | 2026-09-11 | Not Started | Niraj | AMS leadership | Recommendations sequenced
D36 | Phase 3 | WS8 | Agentic AI Infusion and Intervention Inputs | D36 | Giridhar Krishnagiri |  | 2026-09-08 | 2026-09-11 | Not Started | Niraj | AMS leadership | Inputs captured
D37 | Phase 3 | WS8 | Automation Assumptions and Dependencies Register | D37 | Pratik Sathe | Giridhar | 2026-09-08 | 2026-09-11 | Not Started | Giridhar | Automation stakeholders | Register completed
D38 | Phase 3 | WS7 | AMS 2.0 Transformation Roadmap | D38 | Narasimha Murthy | Pooja, Giridhar | 2026-09-04 | 2026-09-18 | Not Started | Ankit / Niraj | Ernesto / AMS leadership | Roadmap endorsed
D39 | Phase 3 | WS7 | Implementation Backlog | D39 | Narasimha Murthy | All owners | 2026-09-08 | 2026-09-18 | Not Started | Niraj | Karol / Tanveer | Backlog packaged
D40 | Phase 3 | WS7 | Quick Win Execution Support Plan | D40 | Shilpi Bhatnagar | Giridhar | 2026-09-08 | 2026-09-18 | Not Started | Niraj | AMS leadership | Quick-win plan packaged
D41 | Phase 3 | WS7 | Executive Readout Deck | D41 | Narasimha Murthy | Ankit, Pratik | 2026-09-12 | 2026-09-18 | Not Started | Ankit/ Niraj | Ernesto / leadership | Readout completed
D42 | Phase 3 | WS7 | Final Handover Package | D42 | Narasimha Murthy | All owners | 2026-09-15 | 2026-09-18 | Not Started | Niraj | Karol / Tanveer | Final package delivered

## Detailed Task Tracker
Task ID | Phase | Workstream | Workstream2 | Activity / Task | Deliverable | Deliverable ID | Primary Owner | Support | Start Date | Due Date | Internal Checkpoint | Status | RAG | Priority | Dependency / Input Needed | Next Action | Due Health | WS1 | WS2 | WS3 | WS4 | WS5 | WS6 | WS7 | WS8
T001 | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | WS1 | Set up internal control tower and single tracker pack | Integrated Project Plan | D02 | Narasimha Murthy | Pooja, Pratik | 2026-06-01 | 2026-06-04 | Internal PMO huddle | In Progress | Green | Must Have | Confirmed team roles | Publish tracker to HCL internal team | Overdue | AMS 2.0 Transformation Charter | Current-State Assessment Summary | AMS Application Support Inventory | AMS RACI Matrix | Future-State Governance Calendar | Capacity and Demand Model | AMS 2.0 Transformation Roadmap | Automation Maturity Assessment Summary
T002 | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | WS1 | Finalize project charter narrative and approval route | AMS 2.0 Transformation Charter | D01 | Niraj Upadhyay | Narasimha, Ankit | 2026-06-03 | 2026-06-10 | Charter QA | In Progress | Green | Must Have | Kickoff feedback and SOW | Issue v1 for review | Overdue | Integrated Project Plan | Current-State Operating View | Application Ownership Matrix | Target Role Profiles | Meeting Rationalization Recommendations | Capacity Heatmap | Implementation Backlog | AI and Automation Opportunity Map
T003 | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | WS1 | Confirm weekly governance rhythm and meeting owners | Integrated Project Plan | D02 | Rathindra Ghosh | Narasimha | 2026-06-03 | 2026-06-06 | Governance setup | In Progress | Green | Must Have | Tanveer / Karol confirmation | Send proposed cadence | Overdue | Data Request / Discovery Tracker | Pain Point and Opportunity Register | ServiceNow Queue / Assignment Group Inventory | Role Gap and Overlap Analysis | Governance Templates | Role / Demand Alignment View | Quick Win Execution Support Plan | Prioritized Automation Recommendations
T004 | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | WS1 | Build and share data discovery tracker structure | Data Request / Discovery Tracker | D03 | Giridhar Krishnagiri | Pooja, Narasimha | 2026-06-04 | 2026-06-09 | Data tracker review | In Progress | Amber | Must Have | Initial source owner list | Create source inventory shell | Overdue | RAID / Action Log | Quick Win Recommendations | Queue-to-App-to-Owner Mapping | AMS 2.0 Operating Model Recommendations | Communication Charter | Capacity Recommendations | Executive Readout Deck | Agentic AI Infusion and Intervention Inputs
T005 | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | WS1 | Develop stakeholder map v0.1 from kickoff deck and org inputs | Integrated Project Plan | D02 | Pooja Kanungo | Narasimha | 2026-06-04 | 2026-06-09 | Stakeholder map review | In Progress | Green | Must Have | Kickoff team list | Map primary vs extended stakeholders | Overdue | Weekly Status Update Template |  | Dashboard and Reporting Inventory |  | AMS KPI Framework |  | Final Handover Package | Automation Assumptions and Dependencies Register
T006 | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | WS1 | Create internal interview and workshop calendar draft | Integrated Project Plan | D02 | Narasimha Murthy | Pooja, Pratik | 2026-06-05 | 2026-06-10 | Calendar review | Not Started | Green | Must Have | Mondelez availability | Draft Tue/Wed/Thu calendar | Overdue | WS3: Governance and Meeting Inventory; WS5: Executive AMS Scorecard Template
T007 | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | WS1 | Prepare first weekly status update template | Weekly Status Update Template | D05 | Rathindra Ghosh | Narasimha | 2026-06-05 | 2026-06-11 | Status QA | Not Started | Green | Should Have | Governance cadence | Draft Week 1 status | Overdue | WS3: Stakeholder Map; WS5: Operational Dashboard Requirements
T008 | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | WS1 | Set up document repository and naming conventions | Data Request / Discovery Tracker | D03 | Narasimha Murthy | Pooja | 2026-06-03 | 2026-06-06 | PMO control | In Progress | Green | Must Have | Collaboration access | Create folder structure | Overdue | WS3: Mondelez AMS Team Profile Inventory
T009 | Phase 1 - Assess & Baseline | WS2 Current-State Baseline | WS2 | Finalize executive and functional lead interview guides | Current-State Operating View | D07 | Shilpi Bhatnagar | Niraj, Giridhar | 2026-06-15 | 2026-06-17 | Interview readiness | Not Started | Green | Must Have | Question bank | Tailor questions by stakeholder | Due <=7d
T010 | Phase 1 - Assess & Baseline | WS2 Current-State Baseline | WS2 | Run AMS leadership discovery interviews | Pain Point and Opportunity Register | D08 | Niraj Upadhyay | Shilpi, Narasimha | 2026-06-16 | 2026-06-26 | Interview playback | Not Started | Green | Must Have | Stakeholder calendar | Schedule Ernesto/Karol/Tanveer inputs | On Track
T011 | Phase 1 - Assess & Baseline | WS2 Current-State Baseline | WS2 | Run AMS functional lead interviews | Pain Point and Opportunity Register | D08 | Shilpi Bhatnagar | Pooja, Pratik | 2026-06-17 | 2026-07-03 | Functional discovery | Not Started | Green | Must Have | Functional lead availability | Prepare pre-reads | On Track
T012 | Phase 1 - Assess & Baseline | WS3 Data Gathering & Inventory Consolidation | WS3 | Collect application inventory sources and CMDB extracts | AMS Application Support Inventory | D10 | Pooja Kanungo | Pratik, Soumya | 2026-06-17 | 2026-07-01 | Data intake | Not Started | Amber | Must Have | CMDB access / exports | Track source availability and gaps | On Track
T013 | Phase 1 - Assess & Baseline | WS3 Data Gathering & Inventory Consolidation | WS3 | Collect ServiceNow queue, assignment group and ticket extracts | ServiceNow Queue / Assignment Group Inventory | D12 | Giridhar Krishnagiri | Narasimha, Soumya | 2026-06-17 | 2026-07-01 | Data intake | Not Started | Amber | Must Have | ServiceNow reporting SME | Request extract fields | On Track
T014 | Phase 1 - Assess & Baseline | WS3 Data Gathering & Inventory Consolidation | WS3 | Create source confidence rating and data gap log | AMS Application Support Inventory | D10 | Giridhar Krishnagiri | Pooja | 2026-06-19 | 2026-07-04 | Data QA | Not Started | Green | Must Have | All incoming data sets | Tag each source as confirmed/inferred/pending | On Track
T015 | Phase 1 - Assess & Baseline | WS2 Current-State Baseline | WS2 | Synthesize pain points from interviews and artefact review | Pain Point and Opportunity Register | D08 | Shilpi Bhatnagar | Pooja, Giridhar | 2026-06-23 | 2026-07-10 | Synthesis huddle | Not Started | Green | Must Have | Interview notes | Create pain point register | On Track
T016 | Phase 1 - Assess & Baseline | WS3 Data Gathering & Inventory Consolidation | WS3 | Build application-to-owner matrix v0.1 | Queue-to-App-to-Owner Mapping | D13 | Pooja Kanungo | Pratik, Soumya | 2026-06-24 | 2026-07-08 | Inventory review | Not Started | Amber | Must Have | CMDB + stakeholder input | Prepare exception list | On Track
T017 | Phase 1 - Assess & Baseline | WS3 Data Gathering & Inventory Consolidation | WS3 | Build queue-to-app-to-owner mapping v0.1 | Queue-to-App-to-Owner Mapping | D13 | Giridhar Krishnagiri | Pooja, Soumya | 2026-06-24 | 2026-07-08 | Queue mapping review | Not Started | Amber | Must Have | ServiceNow queues + app inventory | Map queue gaps | On Track
T018 | Phase 1 - Assess & Baseline | WS5 Governance, Communication & Reporting | WS3 | Inventory current governance forums and reports | Governance and Meeting Inventory | D15 | Rathindra Ghosh | Narasimha, Pooja | 2026-06-24 | 2026-07-10 | Governance discovery | Not Started | Green | Must Have | Governance packs / calendars | Build meeting inventory | On Track
T019 | Phase 1 - Assess & Baseline | WS6 Capacity & Demand Fact Base | WS6 | Build initial demand and workload model structure | Capacity and Demand Model | D29 | Giridhar Krishnagiri | Pratik, Shilpi | 2026-07-01 | 2026-07-15 | Capacity model review | Not Started | Amber | Must Have | Ticket and FTE data | Create demand dimensions | On Track
T020 | Phase 1 - Assess & Baseline | WS2 Current-State Baseline | WS2 | Prepare current-state assessment storyline v0.1 | Current-State Assessment Summary | D06 | Niraj Upadhyay | Shilpi, Pooja, Pratik | 2026-07-08 | 2026-07-17 | Storyline review | Not Started | Green | Must Have | Validated data snippets | Draft executive storyline | On Track
T021 | Phase 1 - Assess & Baseline | WS2 Current-State Baseline | WS2 | Conduct current-state validation workshop | Current-State Operating View | D07 | Niraj Upadhyay | Shilpi, Rathindra, Pratik | 2026-07-21 | 2026-07-23 | Client validation | Not Started | Green | Must Have | Draft findings | Facilitate validation | On Track
T022 | Phase 1 - Assess & Baseline | WS2 Current-State Baseline | WS2 | Lock current-state baseline and quick-win list | Quick Win Recommendations | D09 | Shilpi Bhatnagar | Niraj, Giridhar | 2026-07-22 | 2026-07-24 | Phase 1 gate | Not Started | Green | Must Have | Validation feedback | Update baseline pack | On Track
T023 | Phase 2 - Design & Recommend | WS4 Role Clarity, RACI & Operating Model | WS4 | Draft product-aligned AMS RACI skeleton | AMS RACI Matrix | D18 | Shruthi Chandrashekar | Niraj, Shilpi | 2026-07-27 | 2026-08-05 | RACI design review | Not Started | Green | Must Have | Current-state role insights | Prepare RACI v0.1 | On Track
T024 | Phase 2 - Design & Recommend | WS4 Role Clarity, RACI & Operating Model | WS4 | Facilitate role clarity and handoff workshop | Role Gap and Overlap Analysis | D20 | Shruthi Chandrashekar | Niraj, Pooja | 2026-08-04 | 2026-08-06 | Design workshop | Not Started | Green | Must Have | Role questions and pre-read | Capture gaps/overlaps | On Track
T025 | Phase 2 - Design & Recommend | WS5 Governance, Communication & Reporting | WS5 | Draft governance calendar and forum rationalization | Future-State Governance Calendar | D22 | Rathindra Ghosh | Narasimha | 2026-08-03 | 2026-08-12 | Governance design review | Not Started | Green | Must Have | Governance inventory | Build keep/change/merge/retire view | On Track
T026 | Phase 2 - Design & Recommend | WS5 Governance, Communication & Reporting | WS5 | Define AMS KPI framework and executive scorecard skeleton | AMS KPI Framework | D26 | Rathindra Ghosh | Giridhar, Pratik | 2026-08-06 | 2026-08-17 | KPI review | Not Started | Green | Must Have | Reporting inventory | Build KPI taxonomy | On Track
T027 | Phase 2 - Design & Recommend | WS6 Capacity & Demand Fact Base | WS6 | Develop capacity heatmap and role-demand alignment view | Capacity Heatmap | D30 | Giridhar Krishnagiri | Pratik, Shilpi | 2026-08-03 | 2026-08-20 | Capacity review | Not Started | Amber | Must Have | Ticket, app, FTE, criticality data | Build heatmap and assumptions | On Track
T028 | Phase 2 - Design & Recommend | WS8 AI & Automation Roadmap Advisory | WS8 | Run automation maturity and opportunity scan | Automation Maturity Assessment Summary | D33 | Giridhar Krishnagiri | Soumya, Pratik | 2026-08-10 | 2026-08-24 | Automation advisory review | Not Started | Green | Should Have | Automation/tooling artefacts | Draft opportunity map | On Track
T029 | Phase 2 - Design & Recommend | WS4 Role Clarity, RACI & Operating Model | WS4 | Develop target role profiles and role gap analysis | Target Role Profiles | D19 | Shruthi Chandrashekar | Pooja, Shilpi | 2026-08-10 | 2026-08-21 | Role profile QA | Not Started | Green | Must Have | RACI feedback | Draft role profiles | On Track
T030 | Phase 2 - Design & Recommend | WS4 Role Clarity, RACI & Operating Model | WS4 | Prepare integrated future-state recommendation pack | AMS 2.0 Operating Model Recommendations | D21 | Niraj Upadhyay | Shruthi, Rathindra, Giridhar | 2026-08-17 | 2026-08-28 | Phase 2 storyline review | Not Started | Green | Must Have | RACI, governance, capacity inputs | Build recommendation narrative | On Track
T031 | Phase 2 - Design & Recommend | WS5 Governance, Communication & Reporting | WS5 | Conduct governance and KPI validation workshop | Future-State Governance Calendar | D22 | Rathindra Ghosh | Niraj, Pratik | 2026-08-18 | 2026-08-20 | Client validation | Not Started | Green | Must Have | Governance/KPI drafts | Capture leadership feedback | On Track
T032 | Phase 2 - Design & Recommend | WS4 Role Clarity, RACI & Operating Model | WS4 | Conduct future-state recommendation validation | AMS 2.0 Operating Model Recommendations | D21 | Niraj Upadhyay | Shruthi, Rathindra, Giridhar | 2026-08-25 | 2026-08-27 | Client validation | Not Started | Green | Must Have | Recommendation pack v0.1 | Log open decisions | On Track
T033 | Phase 3 - Roadmap & Handover | WS7 Transformation Roadmap & Execution Support | WS7 | Build 30/60/90/180-day roadmap v0.1 | AMS 2.0 Transformation Roadmap | D38 | Niraj Upadhyay | Narasimha, Shruthi | 2026-08-31 | 2026-09-04 | Roadmap review | Not Started | Green | Must Have | Validated recommendations | Draft roadmap | On Track
T034 | Phase 3 - Roadmap & Handover | WS7 Transformation Roadmap & Execution Support | WS7 | Build implementation backlog with owners and dependencies | Implementation Backlog | D39 | Narasimha Murthy | Niraj, Rathindra | 2026-08-31 | 2026-09-08 | Backlog review | Not Started | Green | Must Have | Roadmap actions | Populate backlog | On Track
T035 | Phase 3 - Roadmap & Handover | WS8 AI & Automation Roadmap Advisory | WS8 | Finalize AI and automation opportunity map and advisory roadmap inputs | AI and Automation Opportunity Map | D34 | Giridhar Krishnagiri | Soumya, Pratik | 2026-09-01 | 2026-09-11 | Automation final review | Not Started | Green | Should Have | Automation maturity inputs | Finalize advisory pack | On Track
T036 | Phase 3 - Roadmap & Handover | WS7 Transformation Roadmap & Execution Support | WS7 | Conduct roadmap prioritization workshop | Implementation Backlog | D39 | Niraj Upadhyay | Narasimha, Shruthi, Giridhar | 2026-09-08 | 2026-09-10 | Client roadmap workshop | Not Started | Green | Must Have | Roadmap v0.1 | Facilitate prioritization | On Track
T037 | Phase 3 - Roadmap & Handover | WS7 Transformation Roadmap & Execution Support | WS7 | Prepare executive readout deck and decision page | Executive Readout Deck | D41 | Niraj Upadhyay | Narasimha, Pratik, Ankit | 2026-09-07 | 2026-09-15 | Executive QA | Not Started | Green | Must Have | Final findings and roadmap | Build readout | On Track
T038 | Phase 3 - Roadmap & Handover | WS7 Transformation Roadmap & Execution Support | WS7 | Assemble final handover package and working files | Final Handover Package | D42 | Narasimha Murthy | All track owners | 2026-09-10 | 2026-09-18 | Handover QA | Not Started | Green | Must Have | Final deliverables | Create final package | On Track
T040 | Phase 3 - Roadmap & Handover | WS7 Transformation Roadmap & Execution Support | WS7 | Conduct executive readout and capture final decisions/open items | Executive Readout Deck | D41 | Ankit Agarwal | Niraj, Narasimha | 2026-09-16 | 2026-09-18 | Executive readout | Not Started | Green | Must Have | Final deck | Lead closure | On Track
Formulas:
Due Health = IF([Status]="Done","Closed",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=7,"Due <=7d","On Track")))

## Lists
Status | Priority | RAG | Phase | Workstream | Stakeholder Level | Cadence
Not Started | Must Have | Green | Phase 0 - Mobilize | WS1 Mobilization & Transformation Structure | Executive | Daily
In Progress | Should Have | Amber | Phase 1 - Assess & Baseline | WS2 Current-State Baseline | AMS Leadership | 2-3x weekly
Blocked | Good to Have | Red | Phase 2 - Design & Recommend | WS3 Data Gathering & Inventory Consolidation | AMS Project Lead | Weekly
Done |  |  | Phase 3 - Roadmap & Handover | WS4 Role Clarity, RACI & Operating Model | AMS Functional Lead | Bi-weekly
Deferred |  |  |  | WS5 Governance, Communication & Reporting | Product / Platform Owner | Milestone-based
|  |  |  | WS6 Capacity & Demand Fact Base | ServiceNow / Reporting SME | As scheduled
|  |  |  | WS7 Transformation Roadmap & Execution Support | Application / Technical SME
|  |  |  | WS8 AI & Automation Roadmap Advisory | Regional Stakeholder